## Slide 1
American Bar Association
Forum on the Construction Industry
2013 Mid Winter Meeting
Plenary 1
Delay Damages
What’s Hot, What’s Not
Dennis A. Estis
Greenbaum, Rowe
Mary Beth Hagan
Hagan & Farrar, PLLC
Dorothy E. Terrell
  Smith Pachter McWhorter, PLC

## Slide 2: TOTAL COST CLAIMS
During the course of a construction project, a number of distinct events delayed the scheduling of the work and increased the contractor’s costs of performance.

## Slide 3: TOTAL COST CLAIMS (cont’d)
Initially, the contractor attempted to keep track of these costs with detailed cost codes, but abandoned that approach before completion of the project because it found it too administratively burdensome.
After completion of the project, the contractor filed a claim seeking damages arising from these delays.

## Slide 4: TOTAL COST CLAIMS (cont’d)
Since it cannot prove its actual costs, can the contractor use the total cost method, or modified total cost method, to prove the amount of its damages?

## Slide 5: TOTAL COST CLAIMS (cont’d)
At trial on a construction delay claim, plaintiff proved that defendant was responsible for the delay but it was impossible to prove its actual losses with specificity.
Accordingly, plaintiff offered evidence in support of a total-cost damages theory.

## Slide 6: TOTAL COST CLAIMS (cont’d)
However, defendant offered evidence that plaintiff’s initial bid was unreasonable and that plaintiff’s total cost was increased by inefficiencies in performance caused by plaintiff.

## Slide 7: TOTAL COST CLAIMS (cont’d)
Can the plaintiff recover damages?
If so, how would they be calculated?

## Slide 8: CUMULATIVE IMPACT CLAIMS
After beginning work on a highway-restoration project under a unit price contract, the contractor encountered an elliptical pipe running across the highway that had not appeared on the drawings.
The existence of this pipe substantially disrupted the project, requiring that the work be restaged so that the work affected by the pipe could be redesigned.

## Slide 9: CUMULATIVE IMPACT CLAIMS (cont’d)
After completion of the work, the contractor files suit seeking damages incurred as a result of the restaging, which the contractor contends delayed its work and rendered its performance less productive and less efficient than anticipated, thereby increasing its costs.

## Slide 10: CUMULATIVE IMPACT CLAIMS (cont’d)
Can the contractor recover damages on a total cost theory?

## Slide 11: CUMULATIVE IMPACT CLAIMS (cont’d)
During the course of a construction project, Owner issued 206 change orders, which, taken together, increased the contract’s dollar value by roughly 12% and extended the performance period by approximately 10%.
Contractor seeks to assert a cumulative impact claim based on the cumulative effect of these changes upon the work.

## Slide 12: CUMULATIVE IMPACT CLAIMS (cont’d)
Are these changes sufficiently disruptive to support a cumulative impact claim?

## Slide 13: HOME OFFICE OVERHEAD
Due to delays caused solely by the Owner, Contractor was substantially delayed in beginning a construction project.
In a subsequent lawsuit, Contractor claims that the delay interrupted its expected cash flow, which interfered with its ability to pay costs associated with its home office overhead, such as salaries, utilities, rent, office equipment, professional dues, travel, accounting and payroll services, and taxes.

## Slide 14: HOME OFFICE OVERHEAD (cont’d)
Can the Contractor recover damages for these overhead costs?
If so, how would those damages be calculated?

## Slide 15: LABOR & EQUIPMENT IMPACT COSTS
When about half of the work on a dam-construction project had been completed, Owner ordered that work on a substantial portion of the dam be suspended pending resolution of a design issue caused solely by the Owner.

## Slide 16: LABOR & EQUIPMENT IMPACT COSTS (cont’d)
After six months, the work was resumed and the project completed. The Contractor claims that the suspension resulted in inefficient use of its labor and equipment.

## Slide 17: LABOR & EQUIPMENT IMPACT COSTS (cont’d)
In particular, Contractor claimed that the inefficiencies arose from:
    Disruption of the normal order of construction and the availability of all of the work at one time, which prevented the efficient movement of workers from task to task.
    Loss of expected improvements in productivity as repetitive tasks were repeated; and
    Low productivity when the suspended work resumed due to loss of experienced workers and supervisors and to normal relearning even by the former workers who returned.

## Slide 18: LABOR & EQUIPMENT IMPACT COSTS (cont’d)
The Contractor submits a claim to recover additional costs caused by these inefficiencies.
How does the Contractor prove its damages?

## Slide 19: LIQUIDATED DAMAGES
A $4.5 million subcontract contains a liquidated damages clause providing that, in the event of an uncured default by Subcontractor, General Contractor is entitled to terminate Subcontractor’s employment and charge “all reasonable costs incurred in this regard (including attorney fees) plus an allowance for administrative burden equal to fifteen percent (15%) to the account of Subcontractor.”

## Slide 20: LIQUIDATED DAMAGES (cont’d)
During the course of the work, Subcontractor A defaulted by failing to complete all of its work and failing to pay all of its suppliers; it did not cure these defaults.
General Contractor paid a second subcontractor, Subcontractor B $3 million to complete Subcontractor A’s work. General Contractor is withholding $450,000 (15% of $3 million) from Subcontractor A’s final payment under the “administrative burden” clause.

## Slide 21: LIQUIDATED DAMAGES (cont’d)
Between the General Contractor and Subcontractor A who is entitled to the $450,000?
Does it matter that General Contractor’s actual costs in overseeing the replacement work were only $85,000?

## Slide 22: LIQUIDATED DAMAGES (cont’d)
A contract contains a liquidated damages clause that specifically provides that “Subcontractor hereby waives any defense as to the validity of any liquidated damages stated in this Agreement as they may appear on the grounds that such liquidated damages are void as penalties or are not reasonably related to actual damages.”

## Slide 23: LIQUIDATED DAMAGES (cont’d)
Is this provision enforceable, or may Subcontractor challenge the enforceability of the liquidated damages provision in a later action?
Should it matter whether this is occurring in a “first look”/“prospective” jurisdiction or a “second look”/“retrospective” jurisdiction?

## Slide 24: DIMINISHED BONDING CAPACITY
Contractor is an established and generally profitable construction company; about half of its revenue comes from public projects that require bonds.

## Slide 25: DIMINISHED BONDING CAPACITY (cont’d)
Contractor entered into a contract to build a new City Hall for City.
The contract called for completion of construction by July 2012, but permitted delays due to inclement weather.
City extended the deadline to October 2012 due to weather delays, but denied future delays due to weather.

## Slide 26: DIMINISHED BONDING CAPACITY (cont’d)
Because the project was not finished in October 2012, City declared Contractor in default and filed a claim with Contractor’s surety.
Contractor claims that as a result of this surety claim, its surety will no longer underwrite bonds for it and it cannot obtain bonds from any other surety in order to bid on public contracts.

## Slide 27: DIMINISHED BONDING CAPACITY (cont’d)
Can Contractor recover from the City Contractor’s lost profits arising from its inability to obtain bonds, and, thus, its inability to bid on public projects?
Does it matter whether the City actually knew that Contractor would be unable to bid on public projects and risk lost profits as a result of diminished bonding capacity?

## Slide 28: EXTENDED FIELD OVERHEAD
In connection with a delay caused solely by Owner, Contractor seeks to recover the additional costs it incurred in having its equipment on site for longer than anticipated.

## Slide 29: EXTENDED FIELD OVERHEAD (cont’d)
Contractor owns the equipment, so it cannot simply offer rental invoices to prove the actual costs incurred.
How does Contractor prove its damages?

## Slide 30: WAIVER OF RIGHT TO DELAY DAMAGES
During the course of a construction project, General Contractor and owner entered into 30 change orders. Each change order was on General Contractor’s form and contained the following language:

## Slide 31: WAIVER OF RIGHT TO DELAY DAMAGES (cont’d)
“Through acceptance of this Change Order, this Subcontractor acknowledges that it has reviewed the progress of the Work related to this Project and the potential impact of the additional work on the progress of the project in the future. As a result, this Change Order includes compensation to the Subcontractor for any and all effects, delays, and inefficiencies or similar demands associated with this Project and the Subcontractor recognizes that there is no basis for any such claim in the future.”

## Slide 32: WAIVER OF RIGHT TO DELAY DAMAGES (cont’d)
After the project is completed, Subcontractor files a complaint seeking delay damages, claiming that its work was unreasonably delayed, interfered with, and impeded by acts and omissions of General Contractor.

## Slide 33: WAIVER OF RIGHT TO DELAY DAMAGES (cont’d)
Can subcontractor recover any delay damages?