## Slide 1
Please Go To
http://ambar.org/plenarypoll
This session is participatory
PSAV - Event Wireless
Login: 1657ABA

## Slide 2: Mock Trial Direct and Cross Examination of the Damages Expert
James Adrian
Adrian International
Ann Greeley
Decision Quest
American Bar Association
Forum on the Construction Industry
2013 Mid Winter Meeting
Daniel D. McMillan
Jones Day
Paul Sandars
Lum, Drasco & Positan
Plenary 6
Richard H. Lowe
Duane Morris

## Slide 3
The Case
Loss of Productivity – Expert Analysis
ACME Constructors v. American Power

## Slide 4
INTRO: QUESTION 1:
Have you previously participated in a mock trial in any capacity?
  Yes
  No
VOTE NOW
Go To
http://ambar.org/plenarypoll

## Slide 5: American Power Project in Peoria IL

## Slide 6: DIRECT AND CROSS EXAMINATION OF THE DAMAGES EXPERT
James Adrian, Ph.D. (Expert) Adrian International, Peoria, IL
Ann T. Greeley, Ph.D (Trial Consultant) DecisionQuest, State College, PA
Richard H. Lowe, Esq. (Judge) Duane Morris, Philadelphia, PA
Daniel D. McMillan, Esq. (Cross-Examination) Jones Day, Los Angeles, CA
Paul Sandars, Esq. (Direct Examination) Lum, Drasco & Positan, Roseland, NJ

## Slide 7
WITNESS James Adrian
Adrian International, Peoria, IL
ATTORNEY Paul Sandars
Lum, Drasco & Positan, Roseland, NJ
Direct Examination

## Slide 8
ACME Constructors v. American Power
Loss of Productivity – Expert Analysis
James J. Adrian, Ph.D., PE, CPA
Professor, Bradley University
President, Adrian International LLC

## Slide 9: Dr. Adrian Engagement
Quantify financial damages (lost productivity craft hours) for ACME owing to owner caused disruptions
Calculate lost labor hours caused by excessive overtime
Calculate lost labor hours caused by cold weather
Calculate lost labor hours caused by sequencing changes and disruption
Calculate lost labor hours caused by loss of learning
Compare my calculated lost craft hours to actual craft hour overrun

## Slide 10: James J. Adrian, Ph.D., PE, CPA CONSTRUCTION PRODUCTIVITY EXPERT
Ph.D. University of Illinois-Urbana, Civil Engineering; Thesis: Measuring Construction Productivity
Author of Three Textbooks on Construction Productivity
Author of Associated General Contractors (AGC) National Construction Productivity Training Course/Manual
Consultant to Project Owners, Designers, and Construction Firms on Measuring and Improving Construction Productivity
Lecturer Worldwide on Measuring and Improving Construction Productivity

## Slide 11: American Power Plant: Major Issues
Added work and constructability issues with Heat Recovery Steam Generator (HRSG’s)
Unanticipated modifications to combustion turbine issue
Turbine building size issues

## Slide 12: EXPERT OPINION
It is my expert opinion that owing to project owner caused disruptions and delays during the construction of the American Power Plant, that ACME Constructors incurred a minimum loss of 136,730 craft hours.
“
”

## Slide 13: Dr. Adrian’s Engagement
Reviewed project drawings
Reviewed accounting reports to include job cost reports and labor reports
Reviewed project estimate
Reviewed project correspondence
Reviewed schedule
Interviewed job site personal
Inspected job site
Participated in job site tour
Conducted on site productivity analysis
Project Documents Reviewed, Personnel Interviewed / Steps Performed
Reviewed temperature, wind, and humidity weather data and expert reports

## Slide 14: Rule 703. Bases of an Expert’s Opinion Testimony
An expert may base an opinion on facts or data in the case that the expert has been made aware of or personally observed. If experts in the particular field would reasonably rely on those kinds of facts or data in forming an opinion on the subject, they need not be admissible for the opinion to be admitted. But if the facts or data would otherwise be inadmissible, the proponent of the opinion may disclose them to the jury only if their probative value in helping the jury evaluate the opinion substantially outweighs the prejudicial effect.

## Slide 15: Conclusions
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs

## Slide 16: Conclusions
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs
Lost Labor Dollars at $52.92 / hour
$2,663,040
$1,650,522
$2,469,671
$452,466
$7,235,699

## Slide 17
Loss of Productivity Due to Unexpected and Excessive Overtime: Dr. Adrian Independent Analysis

## Slide 18: Calculation of Lost Craft Hours Due to Unexpected Overtime on the PPC project
STEP 1: Each worker’s regular time, overtime, and double time determined for each work day and activity: 160,000 daily payroll records!
STEP 2: Based on selection of random labor crafts
STEP 3: Loss productivity factor determined for excessive overtime
STEP 4: Calculation: Lost productivity factor X Hours for each worker → Lost labor hours for any one worker on any one day

## Slide 19: Conclusions
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs

## Slide 20: Shifting HRSG Work Into Winter 2010-2011
Impact on Construction Worker

## Slide 21: Dr. Adrian Calculation of Lost Craft Hours Due to Shifting HRSG Work into the Winter
STEP 1: On site studies: loss of craft hours on cold weather days
STEP 2: Reviewed industry studies on cold weather construction
STEP 3: PPC payroll: each worker’s regular time, overtime, and double time determined for each work day and activity: 160,000 daily payroll records!
STEP 4: Worked with expert meteorologist to list weather data for each day
STEP 5: Weather data used to determine a productivity loss factor for each day for work tasks or cost codes.
STEP 6: Calculation: Lost productivity factor X Hours for each worker → Lost labor hours for any one worker on any one day
The lost hours were summed to yield the total lost hours

## Slide 22: Impact of Cold Weather on Workers Doing HRSG Work
Added time to “warm up” to include walking to heated areas
Added restroom breaks (and walking several hundred feet to heated restrooms)
Lost hours looking for tools and materials in the snow
Time spent chipping ice and snow to be able to work
Time spent constructing insulation barriers
Extended break times to warm up
Added time putting on added clothing
Decrease in productivity from added clothing and gloves
General fatigue associated with working in colder temperatures

## Slide 23: Conclusions: Dr. James Adrian
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs

## Slide 24: Loss of Productivity Due to Sequencing and Disruption:
Dr. Adrian
Independent Analysis

## Slide 25: Conclusions: Dr. James Adrian
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs

## Slide 26: Loss of Productivity Owing to Loss of Learning Due to Need to Accelerate:
Dr. Adrian Analysis

## Slide 27: Conclusions: Dr. James Adrian
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs

## Slide 28: Conclusions: Dr. James Adrian
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs
Lost Labor Dollars at $52.92 / hour
$2,663,040
$1,650,522
$2,469,671
$452,466
$7,235,699

## Slide 29: ACME Labor Hours on Project
Description | Craft hours | 
Actual Craft Hours | 926,000 | 
– Estimated Craft Hours | 580,000 | 
– Approved Change Hours | 148,000 | # of changes = 120
– Unapproved Change Hours | 56,000 | # of changes = 101
= Additional Lost Hours (Total Cost Claim) | 142,000 | Changes, sequencing, weather, added workers, 1820 RFIs, overtime

## Slide 30
DIRECT: QUESTION 1:
Based on what I have heard, the direct helped me to:
A) Strongly favor the plaintiff
B) Slightly favor the plaintiff
C) Slightly favor the defendant
D) Strongly favor the defendant
VOTE NOW
Go To: http://ambar.org/plenarypoll

## Slide 31
DIRECT: QUESTION 2:
The level of testimony was:
A) Too hard to understand
B) Just right
C) Too simplified
VOTE NOW
Go To: http://ambar.org/plenarypoll

## Slide 32
DIRECT: QUESTION 3:
Which of the following is more true of the PowerPoint that was used?
A) It helped to focus my attention
B) It didn’t make a difference
C) It was distracting
VOTE NOW
VOTE NOW
Go To: http://ambar.org/plenarypoll

## Slide 33: Cross Examination
WITNESS James Adrian
Adrian International, Peoria, IL
ATTORNEY Daniel D. McMillan
Jones Day, Los Angeles, CA

## Slide 34: Trial Exhibit 20 Change Order 33: Flue Supports

## Slide 35: Trial Exhibit 20 Change Order 33: Flue Supports
Change Description
Change to Flue Supports.

## Slide 36: Trial Exhibit 20 Change Order 33: Flue Supports
ACME acknowledges and agrees that the compensation set forth in this Change Order comprises the total compensation due to ACME, and all Subcontractors and all Suppliers, for any and all increased costs, acceleration costs, impacts, interruption of schedules, extended overhead costs, delay, ripple effects, or cumulative impacts on all other work that has arisen or may arise as a result of the Flue Support Change.
ACME also agrees to waive all rights, without exception or reservation of any kind whatsoever, to file any further claim or request for equitable adjustment of any type, arising from the Flue Support Change and its impact on any of the remaining work under this Contract.

## Slide 37: Trial Exhibit 20 Change Order 33: Flue Supports
Additionally, we agree that the compensation (time and cost) set forth in this Change Order comprises the total compensation due the Contractor, and all Subcontractors and all Suppliers, for the work or change defined in this Change Order, including all impact on any unchanged work.
The signing of this Change Order shall indicate that the Change constitutes the total equitable adjustment owed the Contractor, all Subcontractors and all Suppliers, [and Contractor] agrees to waive all rights, without exception or reservation of any kind whatsoever, to file any further claim or request for equitable adjustment of any type, for any reasonably foreseeable, cause that shall arise out of or as a result of this Change Order or the impact of this Change Order on the remainder of the work under this Contract.

## Slide 38: Trial Exhibit 1 Construction Contract

## Slide 39: Trial Exhibit 1 Construction Contract
The total change to the Contract Price of any Change Order shall be that indicated on the approved Change Order Form, and such change to the Contract Price shall not be subject to escalation or increase at any time or based upon any theory such as loss of productivity, efficiency, or impact.

## Slide 40: Conclusions: Dr. James Adrian
LOST PRODUCTIVITY DUE TO: | Calculated Lost Labor Hours
Excessive overtime (to speed up construction) | 50,323
Shift of HRSG work to winter 2010-2011 | 31,189
Change of sequencing that caused disruption and congestion | 46,668
Loss of learning (the need to accelerate required hiring more workers) | 8,550
TOTAL | 136,730 hrs
Lost Labor Dollars at $52.92 / hour
$2,663,040
$1,650,522
$2,469,671
$452,466
$7,235,699

## Slide 41
CROSS: QUESTION 1:
Based on what I have heard, the cross helped me to:
A) Strongly favor the plaintiff
B) Slightly favor the plaintiff
C) Slightly favor the defendant
D) Strongly favor the defendant
VOTE NOW
Go To: http://ambar.org/plenarypoll

## Slide 42
CROSS: QUESTION 2:
The Cross:
A) Made me think that the plaintiff is really stretching to get his number
B) Raised some questions in my mind about plaintiff’s number
C) Left me feeling confused
D) Reinforced my sense that plaintiff is
deserving of damages requested
VOTE NOW
VOTE NOW
Go To: http://ambar.org/plenarypoll

## Slide 43
CROSS: QUESTION 3:
The cross-examiner asked the Q’s:
A) Too aggressively
B) Just right
C) Too weakly – I wanted fireworks!
VOTE NOW
Go To: http://ambar.org/plenarypoll

## Slide 44: IN SUMMARY
PANELIST POINTERS

## Slide 45
Welcome Reception
6:00 – 8:00 PM